## Sheet1
category | model name | priority | refrence image | description | file name | completed | modeled | uved | textured | in engine render | estmimated time | actual time | polycount
gnomes
| gnome model 1 | high |  | a model for the gnome enemys
| gnome model 2 | low |  | a model for the gnome enemys
| gnome model 3 | low |  | a model for the gnome enemys
plants
| venus fly trap | high |  | a plant that eats gnomes | Fly_trap_v03 | [5 empty] | 5h | 6h
| datura | medium |  | a plant that hipnosises gnomes
| sunflower | high |  | a plant to upgrade weapons
| cactus | high |  | a plant that has long range projectiles
| rose | medium
weapons
| pistol | high |  | a gun the player starts with to kill gnomes | [6 empty] | 4h | 2.5h
| AR | high |  | a better gun the player can get
| upgraded pistol | medium |  | an upgrade to the pistol | [6 empty] | 1h
| ugraded AR | medium |  | an upgrade to the AR | [6 empty] | 1h
enviroment
| window regular | high |  | modular assets to build the eviroment | [8 empty] | 44
| window big | high |  | modular assets to build the eviroment | [8 empty] | 44
| door | high |  | modular assets to build the eviroment | [8 empty] | 0
| foundation | high |  | modular assets to build the eviroment
| open window | high |  | modular assets to build the eviroment
| smashed window | high |  | modular assets to build the eviroment
| planter | high |  | an area where the player can plant a plant | planter_v01.mb | [5 empty] | 2 hours |  | 769
| fence | high |  | to block the player from gnome spawn
| trees | high |  | hide the gnome spawn
| small plants | high |  | decoration
| metal gate | high |  | buyable door