## Sheet1
category | model name | priority | refrence image | description | file name | completed | modeled | uved | textured | in engine render (current progress) | estmimated time | actual time | polycount
gnomes
| gnome model 1 | high | gnome.jpg | a model for the gnome enemys
| gnome model 2 | low |  | a model for the gnome enemys
| gnome model 3 | low |  | a model for the gnome enemys
plants
| venus fly trap | high | chomper.png | a plant that eats gnomes | Fly_trap_v03.mb |  |  |  |  | Fly_trap_img.jpg | 5h | 6h
| datura | medium |  | a plant that hipnosises gnomes
| sunflower | high | sunflower.jpg | a plant to upgrade weapons
| cactus | high | cactus.jpg | a plant that has long range projectiles
| rose | medium
weapons
| pistol | high |  | a gun the player starts with to kill gnomes | pistol_v03.mb |  |  |  |  | pistol_img.png | 4h | 2.5h
| AR | high |  | a better gun the player can get
| upgraded pistol | medium |  | an upgrade to the pistol | pistol_upgraded_vo1.mb |  |  |  |  | pistol_upgrade_img.png | 1h
| ugraded AR | medium | gun_ar_upgraded.jpg | an upgrade to the AR | [6 empty] | 1h
enviroment
| window regular | high |  | modular assets to build the eviroment | modular_greenhouse_v01 |  |  |  |  | Mod_greenHouse_img.png |  | 0.5 | 44
| window big | high |  | modular assets to build the eviroment | modular_greenhouse_v01 |  |  |  |  | Mod_greenHouse_img.png |  | 0.5 | 44
| door | high |  | modular assets to build the eviroment | modular_greenhouse_v01 | [7 empty] | 0
| foundation | high |  | modular assets to build the eviroment | modular_greenhouse_v01
| open window | high |  | modular assets to build the eviroment | modular_greenhouse_v01
| smashed window | high |  | modular assets to build the eviroment | modular_greenhouse_v01
| planter | high |  | an area where the player can plant a plant | planter_v01.mb |  |  |  |  | planter_textures.png | 2 hours |  | 769
| fence | high |  | to block the player from gnome spawn
| trees | high |  | hide the gnome spawn
| small plants | high |  | decoration
| metal gate | high |  | buyable door
overall
| level | high | greenhouse.jpg | the level made with assets | unreal file |  |  |  |  | level_img.png